## Sheet1
TaskName | Duration | Start | Finish | Name
Yey Buy and Sell
1.Planning
1.1 Planning of System | 1 day | 2018-03-17 | 2018-03-17 | klienth/Rhen
1.2 Planning of Design | 1 day | 2018-03-17 | 2018-03-17 | Ellene
1.3 Flow of System | 2days | 2018-03-17 | 2018-03-20 | klienth
1.4 Programming Language to be use | 1 day | 2018-03-17 | 2018-03-17 | christian
1.5 downloading Visual Studio | 1 day | 2018-03-18 | 2018-03-18 | rhen
2.Creating Windows Form and Design
2.1 Log in Windows Form | 1 day | 2018-03-19 | 2018-03-19 | rhen
2.2registration Windows Form | 1day | 2018-03-19 | 2018-03-19 | christian
2.3 Home Yey Windows Form | 1day | 2018-03-20 | 2018-03-20 | Ellene
2.4 Buyer and Seller UI | 1day | 2018-03-19 | 2018-03-21 | christian
3 Studying C# programming
3.1Connecting into database | 1day | 2018-03-20 | 2018-03-20 | christian
3.2 Log in System | 1day | 2018-03-20 | 2018-03-20 | christian
3.3 Declaring library | 1day | 2018-03-21 | 2018-03-21 | christian
3.4 Uploading photo from the database | 1day | 2018-03-21 | 2018-03-21 | klienth/christian
3.5 Retrieving photo from the database | 3day | 2018-03-21 | 2018-03-23 | klienth
3.6 Updating Information Account | 1day | 2018-03-21 | 2018-03-21 | ellene/rhen
4.Database
4.1 Creating data base for user | 21 day | 2018-03-21 | 3/21/2018 | rhen
4.2 Creating data base for Items/Category | 1 day | 2018-03-21 | 2018-03-21 | rhen
5.C#programming
5.1 Log In System | 1day | 2018-03-22 | 2018-03-22 | christian
5.2 registration System | 1day | 2018-03-22 | 2018-03-22 | christian
5.3Update username and password | 2days | 2018-03-23 | 2018-03-24 | ellene
5.4Welcome Username | 1day | 2018-03-23 | 2018-03-23 | klienth
5.5 Upload image /with information/category | 2 days | 2018-03-22 | 2018-03-23 | rhen/christian
5.6 Retrieve Image/category/combobox | 2 days | 2018-03-22 | 2018-03-23 | christian/klienth
6.Debugging
6.1 Log In System | 1 day | 2018-03-24 | 2018-03-24 | ellene
6.2 registration System | 1day | 2018-03-24 | 2018-03-24 | rhen
6.3Update username and password | 1day | 2018-03-24 | 2018-03-24 | ellene
6.5 Upload image /with information/category | 1day | 2018-03-24 | 2018-03-24 | ellene
6.6 Retrieve Image/category/combobox | 1day | 2018-03-24 | 2018-03-24 | klienth